# 🧠 Login Registration Wizard Epic

1️⃣ Requirements – 8h

Reasonable if:

- Auth type is standard email/password

- No SSO

- No OAuth

- No MFA

- No device trust logic

If you include:

- 2FA

- Email verification flows

- Password strength enforcement

- Rate limiting

- Account lockout policy

Then 8h becomes tight.

Verdict: 8–12h realistic

2️⃣ Mockup & Design – 8h

Fine if:

- You’re reusing a design system

- Desktop UI framework is familiar

If custom animations or state transitions are involved → under.

Verdict: reasonable

3️⃣ API & Service Layer – 24h

This is where realism matters.

Does this include:

- Token storage?

- Refresh token flow?

- Secure local storage?

- Encryption?

- Retry logic?

- Error mapping?

- Offline behavior?

If yes → 24h is slightly optimistic.

Verdict: 28–32h safer

4️⃣ Wizard Implementation – 16h

If it’s:

- Multi-step

- Validation heavy

- Async state changes

- Error mapping to UI

16h might stretch thin.

Verdict: 16–20h

5️⃣ Forgot/Reset – 6h

Often underestimated because:

- Token expiration logic

- Deep linking

- Edge cases when link already used

- UX feedback states

Verdict: 8–10h realistic

6️⃣ Corner Cases – 8h

This is always too low.

Real-world auth corner cases:

- Network failure mid-step

- Token expires during action

- Backend returns 500

- Backend returns malformed error

- Retry race conditions

- Multiple sessions

- User closes app mid-registration

8h is optimistic.

Verdict: 12–16h

📊 Revised Range for Login Epic

Your estimate: 70h

My realistic range:
90–105h

PORTFOLIO EPIC:
✅ No live brokerage integration → no API reliability worries

- ✅ Price updates come from your CSV-driven simulation → no websockets, no streaming edge cases

- ✅ MVP grade → minimal polishing needed

This changes the estimate from my earlier 70h to something much leaner. Let’s recalc realistically.

📊 Portfolio (MVP + CSV simulation)

1️⃣ Requirements – 2–4h

- Define portfolio model

- Define simulation engine input mapping

- Define UI display fields

2–4h is sufficient here. ✅

2️⃣ Mockup + Design – 6h

- Basic table/grid UI, sorting/search/filter minimal

- CSS styling for MVP

6h still fine. ✅

3️⃣ API & Service Layer – 8–10h

- CSV parser

- Map CSV to portfolio holdings

- Provide desktop app with data structure

- Pagination + filtering logic (basic)

✅ With CSV-driven simulation, 8–10h is realistic.

4️⃣ Listing with Pagination – 6h

- Grid/table

- Pagination

- Scroll preservation

- Connect to CSV backend

6h realistic. ✅

5️⃣ Sort / Search / Filters – 4h

- Filter holdings

- Sort columns

- Handle empty results

4h is safe for MVP. ✅

6️⃣ Portfolio Action – 2–3h

- Basic “view details” or “simulate sell/trade” button

- No actual brokerage integration

2–3h fine.

7️⃣ Corner Cases – 4h

- Empty portfolio

- Malformed CSV row

- Zero quantities

- Unexpected data types

4h realistic.

🔢 Revised Total for Portfolio Epic

| Section | Hours |
| --- | --- |
| Requirements | 3 |
| Mockup/Design | 6 |
| Backend/Service | 10 |
| Listing & Pagination | 6 |
| Sort/Search/Filters | 4 |
| Portfolio Actions | 3 |
| Corner Cases | 4 |
| Total | 36h |

🎯 Verdict

- Original estimate: 30h

- My realistic MVP-adjusted estimate: 36h

So your estimate was pretty close, only slightly underestimated.

✅ Low–Medium risk epic because it’s CSV-driven and self-contained.

🛒 Epic 3: Buy/Sell Order Entry Wizard

Your estimate: 32h

Breakdown:

- 4h Requirements & Collaboration

- 6h Mockup & Design

- 18h API & Service Layer Framework

- 2h Submit Action

- 2h Corner Case / Validation

🧠 Assessment

Even with MVP + CSV simulation, this epic is tricky. Let’s break it down.

1️⃣ Requirements – 4h

- You’ll need to define:

  - Order types (Market, Limit, maybe Stop if needed)

  - Input validation (price, quantity, max quantity)

  - Integration with Portfolio (can’t sell more than you own)

  - How the CSV simulation engine consumes orders

  - Submit flow & response handling

4h feels a little tight, but okay for MVP.

✅ Realistic: 4–6h

2️⃣ Mockup & Design – 6h

- Multi-step wizard / single form

- Validation feedback UI

- Disabled/enable logic (e.g., submit only if valid)

6h is reasonable for MVP.

✅ Fine.

3️⃣ API & Service Layer – 18h

Even MVP, you have to:

- Build order model

- Validate order before submission

- Pass order to CSV simulation engine

- Handle async response (simulate fills, errors)

- Update Portfolio holdings after simulated execution

- Handle errors (invalid qty, invalid price, etc.)

- Possibly handle multiple orders simultaneously

18h seems optimistic, because even with CSV simulation, order entry is highly state-dependent.

✅ Realistic: 24–28h

4️⃣ Submit Action – 2h

- Trigger submit

- Update UI on success/failure

- Minimal error handling

2h is okay if your backend/service layer handles most validation. Could go 3–4h safely.

5️⃣ Corner Case / Validation – 2h

This is way too low.

Common edge cases:

- User submits invalid qty

- CSV engine rejects order

- Order submitted while portfolio is mid-update

- Rapid repeated clicks (duplicate submission)

- Negative price or zero quantity

- Race conditions in UI vs portfolio update

✅ Realistic: 6–8h

🔢 Revised Estimate for Buy/Sell Order Entry

| Section | Hours |
| --- | --- |
| Requirements | 5 |
| Mockup/Design | 6 |
| API & Service Layer | 26 |
| Submit Action | 3 |
| Corner Cases | 6 |
| Total | 46h |

🎯 Verdict

- Your estimate: 32h

- Realistic MVP: 46h

This epic is high-risk for MVP. Even with CSV simulation, the state consistency between Portfolio, Order Entry, and the CSV engine is non-trivial.

📚 Epic 4: Order Book

Your estimate: 28h

Breakdown:

- 2h Requirements & Collaboration

- 6h Mockup/Design/ CSS

- 10h API & Service Layer

- 8h Overview & Details

- 2h Corner Cases

🧠 Assessment

Even with MVP + CSV simulation, the Order Book is tricky because it’s the state hub for executed orders and needs to reflect changes in near real-time.

1️⃣ Requirements – 2h

- Define data model: open orders, filled orders, partial fills

- Define columns & filters

- Define how simulation engine sends executed orders

2h is a bit tight. Realistically: 3–4h

2️⃣ Mockup/Design – 6h

- Table/grid UI

- Tabs for open/filled/cancelled orders

- Highlight changes

- Minimal styling

6h is reasonable for MVP. ✅

3️⃣ API & Service Layer – 10h

Even with CSV simulation:

- Pull executed orders from simulation engine

- Map to desktop UI model

- Support filtering/sorting

- Update portfolio totals dynamically

10h might be slightly optimistic. Realistic: 12–14h

4️⃣ Overview & Details – 8h

- Clicking an order shows detail

- Partial fill info

- Status updates

8h is fine for MVP if details are simple.

5️⃣ Corner Cases – 2h

Underestimated. Edge cases include:

- Empty order book

- Orders submitted simultaneously

- Orders rejected by simulation engine

- Data mismatch between order book & portfolio

Realistic: 4–6h

🔢 Revised Estimate

| Section | Hours |
| --- | --- |
| Requirements | 3 |
| Mockup/Design | 6 |
| API & Service Layer | 14 |
| Overview & Details | 8 |
| Corner Cases | 5 |
| Total | 36h |

🎯 Verdict

- Your estimate: 28h

- Realistic MVP: 36h

Even MVP needs careful handling here — the order book is the glue between orders and portfolio.

📊 Epic 5: Depth of Market (Ladder Trader) — Revised

Your estimate: 26h

New breakdown including Requirements & Collaboration (2h):

- 2h Requirements & Collaboration

- 6h Mockup, Design & CSS

- 10h API & Service Layer

- 8h Overview & Details

- 2h Corner Cases

🧠 Assessment with updated story

1️⃣ Requirements & Collaboration – 2h

- Define ladder model: bids, asks, spreads

- How it connects to order entry & portfolio

- User interaction: click-to-trade, highlight active prices

- Decide update frequency for simulation engine

2h is minimal, but MVP-grade. ✅

2️⃣ Mockup, Design & CSS – 6h

- Table/grid showing price ladder

- Bid/ask highlighting

- Active orders overlay

- Color-coding for best bid/ask

If MVP is basic grid, 6h is reasonable. Realistically, could stretch to 8h if UI tweaks needed.

3️⃣ API & Service Layer – 10h

- Map CSV simulation engine to ladder structure

- Handle order placement/cancellation

- Keep ladder & order book state consistent

- Update portfolio totals after order execution

Even MVP, this is underestimated. Realistic: 16–18h

4️⃣ Overview & Details – 8h

- Price-level interactions

- Show order details on click

- Highlight spreads and last traded price

8h is okay for MVP. ✅

5️⃣ Corner Cases – 2h

- Missing price levels in CSV

- Rapid updates

- Orders overlapping same price level

- State mismatch with portfolio/order book

2h is low. Realistic: 6h

🔢 Revised Total

| Section | Hours |
| --- | --- |
| Requirements & Collaboration | 2 |
| Mockup/Design | 8 |
| API & Service Layer | 18 |
| Overview/Details | 8 |
| Corner Cases | 6 |
| Total | 42h |

🎯 Verdict

- Original estimate: 26h

- MVP realistic with updated requirement story: ~42h

Adding the 2h requirement story didn’t just increase time directly; it also highlights that planning and defining interactions upfront is critical, especially for ladder trading.

📊 Epic 6: Trading Charts (Candle)

Your estimate: 28h

Breakdown:

- 2h Requirements & Collaboration

- 6h Mockup, Design & CSS

- 10h API & Service Layer

- 8h OHLCV Charts for each stock

- 2h Corner Cases

🧠 Assessment

Even with CSV simulation, charts have some tricky aspects:

- Data mapping – OHLCV data needs proper parsing and aggregation from CSV.

- Chart rendering – Candlestick rendering, scaling axes, zoom, pan.

- Performance – Multiple stocks may need multiple chart instances.

- UI interactions – Hover info, tooltips, selecting timeframe.

- Corner cases – Empty data, malformed CSV, missing timeframes.

1️⃣ Requirements & Collaboration – 2h

- Define which timeframes to support (1m, 5m, daily)

- Decide chart interactions (hover, zoom, pan)

✅ 2h is fine for MVP.

2️⃣ Mockup, Design & CSS – 6h

- Layout of candlestick chart

- Minimal styling, axis labels, colors

✅ 6h reasonable for MVP.

3️⃣ API & Service Layer – 10h

- Map CSV data to chart library format

- Provide filtered timeframes

- Hook chart updates to simulation engine

10h is reasonable if you use an existing chart library.
If custom drawing: could go 12–14h.

4️⃣ OHLCV Charts for Each Stock – 8h

- Multiple stocks displayed

- Updates as simulation runs

- Zoom/pan/timeframe switching

8h is okay for MVP with a library.
Custom rendering: 12h.

5️⃣ Corner Cases – 2h

- Empty CSV

- Missing time points

- Division by zero in P/L

- Malformed rows

2h is tight. Realistic: 4–6h

🔢 Revised Total

| Section | Hours |
| --- | --- |
| Requirements | 2 |
| Mockup/Design | 6 |
| API & Service Layer | 10 |
| Chart Rendering | 8 |
| Corner Cases | 5 |
| Total | 31h |

🎯 Verdict

- Your estimate: 28h

- MVP realistic: ~31h

With a library and CSV simulation, this is low-risk but UI-heavy. Performance testing is minimal if simulation is small.

📊 Epic 7: My Profile

Your estimate: 58h

Breakdown:

- 2h Requirements & Collaboration

- 4h Mockup & Design

- 24h API & Service Layer

- 16h Overview & Details

- 8h Security Settings

- 2h Profile Actions

- 2h Corner Cases

🧠 Assessment

Even for MVP, profile management involves sensitive data and multiple states, so some caution is needed.

1️⃣ Requirements & Collaboration – 2h

- Define user profile fields (name, email, preferences)

- Security settings (password change, optionally 2FA in future)

- Profile action definitions (update avatar, update preferences)

✅ 2h is realistic for MVP.

2️⃣ Mockup & Design – 4h

- Basic form layout

- Tabs for security, personal info

- Minimal CSS

✅ 4h is fine for MVP.

3️⃣ API & Service Layer – 24h

- Implement CRUD for profile

- Handle validation on update

- Password hashing & change flows

- Security settings storage (MVP: simple storage)

- Integration with Login & Portfolio for consistency

24h seems reasonable. Could stretch to 28h if you want robust error handling.

4️⃣ Overview & Details – 16h

- Display profile info

- Display security settings

- Allow edits

- Confirmations / validation

✅ 16h is realistic.

5️⃣ Security Settings – 8h

- Password change

- Optional 2FA prep

- Local encryption for storage (since secure storage isn’t solved)

8h is reasonable. Could be tight depending on encryption method.

6️⃣ Profile Actions – 2h

- Save/update profile

- Reset preferences

✅ 2h fine for MVP.

7️⃣ Corner Cases – 2h

- Invalid input

- Partial updates

- Network failure (for API)

2h is optimistic. Realistic: 4h

🔢 Revised Total

| Section | Hours |
| --- | --- |
| Requirements | 2 |
| Mockup/Design | 4 |
| API & Service Layer | 24 |
| Overview/Details | 16 |
| Security Settings | 8 |
| Profile Actions | 2 |
| Corner Cases | 4 |
| Total | 60h |

🎯 Verdict

- Your estimate: 58h

- MVP realistic: ~60h

Profile epic is medium risk, mostly due to security and state consistency with login & portfolio.